## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 5) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2017-10-22 | 2017-10-23 | 2017-09-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10
|  |  |  | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 143 | 134 | 125 | 116 | 107 | 98 | 89 | 80 | 71 | 62 | 53 | 44 | 35 | 26 | 17 | 8 | -1 | -10 | -19 | -28 | 0 | Ideal Burndown
|  |  | 200 | Week #1 (10 hrs / week) D1: 150; Week #1 (10 hrs / week) D2: 146; Week #1 (10 hrs / week) D3: 145; Week #1 (10 hrs / week) D4: 141; Week #1 (10 hrs / week) D5: 137; Week #1 (10 hrs / week) D6: 135; Week #1 (10 hrs / week) D7: 131; Week #2 (10 hrs / week) D8: 0; Week #2 (10 hrs / week) D9: 0; Week #2 (10 hrs / week) D10: 0; Week #2 (10 hrs / week) D11: 0 | Remaining Hrs (Total)
Implementation of shopping cart | Design and implement users and sessions | Manasi | 20 | Week #1 (10 hrs / week) D1: 20; Week #1 (10 hrs / week) D2: 18; Week #1 (10 hrs / week) D3: 18; Week #1 (10 hrs / week) D4: 17; Week #1 (10 hrs / week) D5: 17; Week #1 (10 hrs / week) D6: 17; Week #1 (10 hrs / week) D7: 17
| Design and implement product catalog | Divya | 20 | Week #1 (10 hrs / week) D1: 20; Week #1 (10 hrs / week) D2: 19; Week #1 (10 hrs / week) D3: 19; Week #1 (10 hrs / week) D4: 18; Week #1 (10 hrs / week) D5: 18; Week #1 (10 hrs / week) D6: 18; Week #1 (10 hrs / week) D7: 18
Implementation of shopping cart | Design and implement shopping cart | Pooja | 20 | Week #1 (10 hrs / week) D1: 20; Week #1 (10 hrs / week) D2: 20; Week #1 (10 hrs / week) D3: 20; Week #1 (10 hrs / week) D4: 19; Week #1 (10 hrs / week) D5: 17; Week #1 (10 hrs / week) D6: 17; Week #1 (10 hrs / week) D7: 16
| Design and implement recommendations | Varun | 20 | Week #1 (10 hrs / week) D1: 20; Week #1 (10 hrs / week) D2: 20; Week #1 (10 hrs / week) D3: 19; Week #1 (10 hrs / week) D4: 18; Week #1 (10 hrs / week) D5: 18; Week #1 (10 hrs / week) D6: 18; Week #1 (10 hrs / week) D7: 18
| Design and implement payment | Anjana | 20 | Week #1 (10 hrs / week) D1: 20; Week #1 (10 hrs / week) D2: 19; Week #1 (10 hrs / week) D3: 19; Week #1 (10 hrs / week) D4: 19; Week #1 (10 hrs / week) D5: 17; Week #1 (10 hrs / week) D6: 17; Week #1 (10 hrs / week) D7: 16
| Users and catalog integration | Manasi | 10 | Week #1 (10 hrs / week) D1: 10; Week #1 (10 hrs / week) D2: 10; Week #1 (10 hrs / week) D3: 10; Week #1 (10 hrs / week) D4: 10; Week #1 (10 hrs / week) D5: 10; Week #1 (10 hrs / week) D6: 10; Week #1 (10 hrs / week) D7: 9
| Catalog and recommendation integration | Varun | 10 | Week #1 (10 hrs / week) D1: 10; Week #1 (10 hrs / week) D2: 10; Week #1 (10 hrs / week) D3: 10; Week #1 (10 hrs / week) D4: 10; Week #1 (10 hrs / week) D5: 10; Week #1 (10 hrs / week) D6: 10; Week #1 (10 hrs / week) D7: 10
| Cart and payment integration | Anjana | 10 | Week #1 (10 hrs / week) D1: 10; Week #1 (10 hrs / week) D2: 10; Week #1 (10 hrs / week) D3: 10; Week #1 (10 hrs / week) D4: 10; Week #1 (10 hrs / week) D5: 10; Week #1 (10 hrs / week) D6: 10; Week #1 (10 hrs / week) D7: 10
UML Class Design | Main user class diagram | Divya | 10 | Week #1 (10 hrs / week) D1: 10; Week #1 (10 hrs / week) D2: 10; Week #1 (10 hrs / week) D3: 10; Week #1 (10 hrs / week) D4: 10; Week #1 (10 hrs / week) D5: 10; Week #1 (10 hrs / week) D6: 10; Week #1 (10 hrs / week) D7: 9
| Multiuser class diagram | Pooja | 10 | Week #1 (10 hrs / week) D1: 10; Week #1 (10 hrs / week) D2: 10; Week #1 (10 hrs / week) D3: 10; Week #1 (10 hrs / week) D4: 10; Week #1 (10 hrs / week) D5: 10; Week #1 (10 hrs / week) D6: 8; Week #1 (10 hrs / week) D7: 8
Team:
Anjana | 10 hours / Week
Divya | 10 hours / Week
Manasi | 10 hours / Week
Pooja | 10 hours / Week
Varun | 10 hours / Week
Total Available Hours During Sprint: | 200